## Product Backlog
Story ID | Epic ID | Epic | User Story | Priority | Story Points | Status | FRD Requirement | API / System Area | Business Owner
US-EMP-001 | EPIC-01 | Workforce & Employee Management | As an HR user, I want to create an employee record so that employee information is centrally maintained. | High | 5 | Implemented | FR-EMP-001 | /api/employees | HR
US-EMP-002 | EPIC-01 | Workforce & Employee Management | As an HR user, I want to retrieve employee information so that I can view current workforce details. | High | 3 | Implemented | FR-EMP-002 | /api/employees | HR
US-EMP-003 | EPIC-01 | Workforce & Employee Management | As an HR user, I want to update employee information so that employee records remain current. | High | 3 | Implemented | FR-EMP-003 | /api/employees | HR
US-EMP-004 | EPIC-01 | Workforce & Employee Management | As an HR user, I want to update employee lifecycle status so that employment changes are recorded accurately. | High | 3 | Implemented | FR-EMP-004 | /api/employees/:id/status | HR
US-EMP-005 | EPIC-01 | Workforce & Employee Management | As an HR or business manager, I want department-specific active status calculated so that workforce activity is represented according to business rules. | Critical | 5 | Implemented | FR-EMP-005 | /api/employees | HR / Operations / Finance
US-DEPT-001 | EPIC-01 | Workforce & Employee Management | As an HR user, I want to maintain departments so that employees and organizational reporting use valid department information. | High | 3 | Implemented | FR-DEPT-001 | /api/departments | HR
US-ROLE-001 | EPIC-01 | Workforce & Employee Management | As an HR user, I want to maintain job roles so that employees and recruitment activities use valid roles. | High | 3 | Implemented | FR-ROLE-001 | /api/job-roles | HR
US-WORK-001 | EPIC-01 | Workforce & Employee Management | As an HR user, I want to maintain work statuses so that employee workforce states are consistently recorded. | High | 3 | Implemented | FR-WORK-001 | /api/work-statuses | HR
US-ATT-001 | EPIC-02 | Attendance & Leave | As an HR or Operations user, I want to record employee attendance so that workforce attendance can be monitored. | High | 5 | Implemented | FR-ATT-001 | /api/attendance | Operations
US-ATT-002 | EPIC-02 | Attendance & Leave | As an HR or Operations user, I want to retrieve attendance records so that attendance history can be reviewed. | Medium | 3 | Implemented | FR-ATT-002 | /api/attendance | Operations
US-ATT-003 | EPIC-02 | Attendance & Leave | As an HR or Operations user, I want working hours recorded so that operational attendance analytics can be generated. | Medium | 3 | Implemented | FR-ATT-003 | /api/attendance | Operations
US-LEAVE-001 | EPIC-02 | Attendance & Leave | As an employee or HR user, I want to submit a leave request so that leave can be formally recorded. | High | 5 | Implemented | FR-LEAVE-002 | /api/leave-requests | HR
US-LEAVE-002 | EPIC-02 | Attendance & Leave | As an HR or manager, I want to approve or reject leave requests so that leave decisions are formally recorded. | High | 5 | Implemented | FR-LEAVE-003 | /api/leave-requests | HR / Managers
US-LEAVE-003 | EPIC-02 | Attendance & Leave | As an HR user, I want to maintain leave types so that organizational leave policies can be configured. | Medium | 3 | Implemented | FR-LEAVE-001 | /api/leave-types | HR
US-PERF-001 | EPIC-03 | Performance & PIP | As an HR or manager, I want to record performance reviews so that employee performance can be evaluated and tracked. | High | 5 | Implemented | FR-PERF-001 | /api/performance-reviews | HR / Managers
US-PERF-002 | EPIC-03 | Performance & PIP | As an HR or manager, I want to view performance history so that employee development can be monitored over time. | Medium | 3 | Implemented | FR-PERF-002 | /api/performance-reviews | HR / Managers
US-PIP-001 | EPIC-03 | Performance & PIP | As an HR or manager, I want to create a Performance Improvement Plan so that performance improvement activities are formally tracked. | High | 5 | Implemented | FR-PIP-001 | /api/pips | HR / Managers
US-PIP-002 | EPIC-03 | Performance & PIP | As an HR or manager, I want to track PIP status and progress so that improvement activities remain visible. | High | 3 | Implemented | FR-PIP-002 | /api/pips | HR / Managers
US-TRAIN-001 | EPIC-04 | Learning & Development | As an HR or training user, I want to maintain training programs so that available learning programs are centrally managed. | High | 3 | Implemented | FR-TRAIN-001 | /api/training-programs | HR / Training
US-TRAIN-002 | EPIC-04 | Learning & Development | As an HR or training user, I want to enroll employees into training so that employee participation can be tracked. | High | 5 | Implemented | FR-TRAIN-002 | /api/employee-training | HR / Training
US-TRAIN-003 | EPIC-04 | Learning & Development | As an HR or training user, I want to record training completion and scores so that learning outcomes can be measured. | Medium | 3 | Implemented | FR-TRAIN-003 | /api/employee-training | HR / Training
US-TRAIN-004 | EPIC-04 | Learning & Development | As an HR manager, I want training analytics so that employee learning participation and outcomes can be monitored. | Medium | 3 | Implemented | FR-TRAIN-004 | /api/analytics/training | HR / Management
US-REC-001 | EPIC-05 | Recruitment | As a recruiter, I want to create candidate records so that prospective employees can be managed through a centralized pipeline. | High | 5 | Implemented | FR-REC-001 | /api/candidates | Recruitment
US-REC-002 | EPIC-05 | Recruitment | As a recruiter, I want to update candidate status so that candidate progress through recruitment stages is visible. | High | 3 | Implemented | FR-REC-002 | /api/candidates | Recruitment
US-REC-003 | EPIC-05 | Recruitment | As a recruiter, I want to create job applications so that candidates can be associated with specific job roles. | High | 5 | Implemented | FR-REC-003 | /api/job-applications | Recruitment
US-REC-004 | EPIC-05 | Recruitment | As a recruiter, I want to manage application status so that recruitment pipeline progress is tracked. | High | 3 | Implemented | FR-REC-004 | /api/job-applications | Recruitment
US-REC-005 | EPIC-05 | Recruitment | As a recruiter, I want to schedule interviews so that candidate interviews are formally managed. | High | 5 | Implemented | FR-REC-005 | /api/interviews | Recruitment
US-REC-006 | EPIC-05 | Recruitment | As an interviewer, I want to record interview ratings and feedback so that interview outcomes are documented. | High | 3 | Implemented | FR-REC-006 | /api/interviews | Recruitment / Interviewer
US-REC-007 | EPIC-05 | Recruitment | As a recruiter, I want to create job offers so that selected candidates can receive formal offers. | High | 5 | Implemented | FR-REC-007 | /api/job-offers | Recruitment
US-REC-008 | EPIC-05 | Recruitment | As a recruiter, I want to update offer status so that the offer lifecycle can be tracked. | High | 3 | Implemented | FR-REC-008 | /api/job-offers | Recruitment
US-REC-009 | EPIC-05 | Recruitment | As an HR or recruiter, I want accepted offers to be traceable to employee onboarding so that the recruitment-to-employee lifecycle is connected. | Medium | 5 | Planned | FR-REC-010 | Recruitment + Employees | HR / Recruitment
US-AN-001 | EPIC-06 | Analytics & BI | As an HR or management user, I want an HR overview dashboard so that key workforce indicators can be monitored. | Critical | 5 | Implemented | FR-AN-001 | /api/analytics/overview | Management / HR
US-AN-002 | EPIC-06 | Analytics & BI | As a management user, I want department analytics so that workforce information can be analyzed by department. | High | 5 | Implemented | FR-AN-002 | /api/analytics/departments | Management / HR
US-AN-003 | EPIC-06 | Analytics & BI | As an HR or management user, I want attendance analytics so that workforce attendance trends can be monitored. | High | 3 | Implemented | FR-AN-003 | /api/analytics/attendance | Management / HR
US-AN-004 | EPIC-06 | Analytics & BI | As an HR or management user, I want leave analytics so that leave utilization can be monitored. | Medium | 3 | Implemented | FR-AN-004 | /api/analytics/leave | Management / HR
US-AN-005 | EPIC-06 | Analytics & BI | As an HR or management user, I want performance analytics so that employee performance information can be analyzed. | Medium | 3 | Implemented | FR-AN-005 | /api/analytics/performance | Management / HR
US-AN-006 | EPIC-06 | Analytics & BI | As an HR or management user, I want training analytics so that employee development activity can be analyzed. | Medium | 3 | Implemented | FR-AN-006 | /api/analytics/training | Management / HR
US-AN-007 | EPIC-06 | Analytics & BI | As a recruitment manager, I want recruitment analytics so that candidate and hiring pipeline activity can be monitored. | High | 3 | Implemented | FR-AN-007 | /api/analytics/recruitment | Recruitment / Management
US-API-001 | EPIC-07 | Platform API & Data | As an application user, I want validated REST APIs so that HR360 transactions are processed consistently. | High | 5 | Implemented | FR-API-001 | REST APIs | Application Owner
US-API-002 | EPIC-07 | Platform API & Data | As an application user, I want invalid requests to return controlled errors so that data quality and system reliability are maintained. | High | 3 | Implemented | FR-API-002 | REST APIs | Application Owner
US-API-003 | EPIC-07 | Platform API & Data | As an application owner, I want HR data persisted with referential integrity so that related records remain consistent. | High | 5 | Implemented | FR-DB-001 / FR-DB-002 | PostgreSQL | Application Owner
US-API-004 | EPIC-07 | Platform API & Data | As an application owner, I want sensitive configuration protected so that database credentials and secrets are not exposed. | Critical | 3 | Implemented | FR-SEC-001 / FR-SEC-002 | Backend / .env | Application Owner

## Acceptance Criteria
AC ID | Story ID | Acceptance Criteria | Given | When | Then | Test Type
AC-EMP-001 | US-EMP-001 | Valid employee data can be created | Given valid employee master data is provided | When the employee creation request is submitted | Then a new employee record is created successfully | Functional
AC-EMP-002 | US-EMP-001 | Employee code must be unique | Given an existing employee code | When another employee uses the same code | Then the system rejects the request | Negative
AC-EMP-003 | US-EMP-002 | Employee details are retrievable | Given an existing employee | When the employee endpoint is requested | Then the employee details are returned | Functional
AC-EMP-004 | US-EMP-003 | Employee updates are persisted | Given an existing employee | When valid employee information is updated | Then the updated values are persisted | Functional
AC-EMP-005 | US-EMP-004 | Employee lifecycle status can be changed | Given an existing employee | When an authorized status update is submitted | Then the employee lifecycle status is updated | Functional
AC-EMP-006 | US-EMP-005 | HR active rule is applied | Given an employee belongs to HR | When employment status is EMPLOYED | Then department_active_status is ACTIVE | Business Rule
AC-EMP-007 | US-EMP-005 | Operations active rule is applied | Given an employee belongs to Operations | When work status is WORKING or ONLINE | Then department_active_status is ACTIVE | Business Rule
AC-EMP-008 | US-EMP-005 | Finance active rule is applied | Given an employee belongs to Finance | When salary status is PAID | Then department_active_status is ACTIVE | Business Rule
AC-EMP-009 | US-EMP-005 | Inactive condition is calculated | Given an employee does not satisfy the applicable active rule | When employee information is retrieved | Then department_active_status is NOT ACTIVE | Business Rule
AC-DEPT-001 | US-DEPT-001 | Department can be created | Given valid department data | When the create request is submitted | Then the department is created | Functional
AC-DEPT-002 | US-DEPT-001 | Department can be updated | Given an existing department | When valid changes are submitted | Then the department is updated | Functional
AC-ROLE-001 | US-ROLE-001 | Job role can be maintained | Given valid job-role information | When the role request is submitted | Then the job role is created or updated | Functional
AC-WORK-001 | US-WORK-001 | Work statuses use approved values | Given a work status request | When the status is submitted | Then only valid configured statuses are accepted | Validation
AC-ATT-001 | US-ATT-001 | Attendance can be recorded | Given a valid employee and attendance data | When attendance is submitted | Then the attendance record is stored | Functional
AC-ATT-002 | US-ATT-001 | Invalid attendance status is rejected | Given an invalid attendance status | When the attendance request is submitted | Then the request is rejected | Negative
AC-ATT-003 | US-ATT-003 | Working hours are stored | Given valid attendance information | When working hours are submitted | Then working hours are persisted | Functional
AC-LEAVE-001 | US-LEAVE-001 | Leave request can be submitted | Given valid employee and leave information | When the leave request is submitted | Then a leave request is created | Functional
AC-LEAVE-002 | US-LEAVE-002 | Leave can be approved | Given a pending leave request | When an authorized user approves it | Then the status changes to APPROVED | Functional
AC-LEAVE-003 | US-LEAVE-003 | Leave type can be maintained | Given valid leave type data | When the request is submitted | Then the leave type is created or updated | Functional
AC-PERF-001 | US-PERF-001 | Performance review can be recorded | Given valid employee review data | When the review is submitted | Then the performance review is stored | Functional
AC-PERF-002 | US-PERF-002 | Performance history is retrievable | Given an employee with previous reviews | When performance history is requested | Then applicable review records are returned | Functional
AC-PIP-001 | US-PIP-001 | PIP can be created | Given valid employee and PIP information | When the PIP is submitted | Then a PIP record is created | Functional
AC-PIP-002 | US-PIP-002 | PIP status can be tracked | Given an existing PIP | When the PIP status is updated | Then the updated status is persisted | Functional
AC-TRAIN-001 | US-TRAIN-001 | Training program can be created | Given valid training program data | When the request is submitted | Then the training program is created | Functional
AC-TRAIN-002 | US-TRAIN-002 | Employee can be enrolled | Given an existing employee and training program | When enrollment is submitted | Then an employee-training record is created | Functional
AC-TRAIN-003 | US-TRAIN-003 | Training completion can be recorded | Given an enrolled employee | When completion information is submitted | Then completion status and applicable score are stored | Functional
AC-TRAIN-004 | US-TRAIN-004 | Training analytics are calculated | Given employee training records | When training analytics are requested | Then training counts and applicable score metrics are returned | Analytics
AC-REC-001 | US-REC-001 | Candidate can be created | Given valid candidate information | When the candidate is submitted | Then a candidate record is created | Functional
AC-REC-002 | US-REC-002 | Candidate status can be updated | Given an existing candidate | When a valid status is submitted | Then the candidate status is updated | Functional
AC-REC-003 | US-REC-003 | Application can be created | Given a valid candidate and job role | When the application is submitted | Then an application record is created | Functional
AC-REC-004 | US-REC-003 | Duplicate application is prevented | Given an existing candidate-job-role application | When the same combination is submitted again | Then the duplicate application is rejected | Negative
AC-REC-005 | US-REC-004 | Application status can be updated | Given an existing application | When a valid status is submitted | Then the application status is updated | Functional
AC-REC-006 | US-REC-005 | Interview can be scheduled | Given an existing application | When valid interview details are submitted | Then an interview record is created | Functional
AC-REC-007 | US-REC-006 | Interview outcome can be recorded | Given a completed interview | When rating and feedback are submitted | Then the interview outcome is stored | Functional
AC-REC-008 | US-REC-007 | Job offer can be created | Given an eligible application | When valid offer information is submitted | Then a job offer is created | Functional
AC-REC-009 | US-REC-008 | Offer status can be updated | Given an existing job offer | When a valid offer status is submitted | Then the offer status is updated | Functional
AC-REC-010 | US-REC-007 | Invalid salary is rejected | Given an offer salary less than or equal to zero | When the offer is submitted | Then the system rejects the offer | Negative
AC-REC-011 | US-REC-009 | Accepted offer remains traceable | Given an accepted job offer | When the future employee transition is performed | Then candidate, application, offer and employee records remain traceable | Planned
AC-AN-001 | US-AN-001 | Overview analytics are available | Given valid HR data | When the overview endpoint is requested | Then configured workforce KPIs are returned | Analytics
AC-AN-002 | US-AN-002 | Department analytics are available | Given employee and department data | When department analytics are requested | Then department-level metrics are returned | Analytics
AC-AN-003 | US-AN-003 | Attendance analytics are available | Given attendance records | When attendance analytics are requested | Then attendance metrics are returned | Analytics
AC-AN-004 | US-AN-004 | Leave analytics are available | Given leave records | When leave analytics are requested | Then leave metrics are returned | Analytics
AC-AN-005 | US-AN-005 | Performance analytics are available | Given performance reviews | When performance analytics are requested | Then performance metrics are returned | Analytics
AC-AN-006 | US-AN-006 | Training analytics are available | Given training records | When training analytics are requested | Then training metrics are returned | Analytics
AC-AN-007 | US-AN-007 | Recruitment analytics are available | Given candidate and recruitment data | When recruitment analytics are requested | Then recruitment pipeline metrics are returned | Analytics
AC-API-001 | US-API-001 | REST APIs process valid requests | Given a valid API request | When the request reaches the backend | Then the applicable operation is executed | Integration
AC-API-002 | US-API-002 | Invalid requests return controlled errors | Given invalid request data | When the request is submitted | Then the API returns an appropriate error response | Negative
AC-API-003 | US-API-003 | Related records maintain integrity | Given related HR records | When a transaction is persisted | Then database relationships remain valid | Integration
AC-API-004 | US-API-004 | Secrets remain protected | Given application configuration contains credentials | When the application runs | Then credentials are not exposed through source control or API responses | Security

## Sprint Backlog
Sprint ID | Sprint Name | Objective | Story ID | Status | Owner | Planned/Completed
SPR-01 | Foundation & Database | Establish project structure, PostgreSQL and backend foundation | US-API-003 | Completed | Nida Khan | Completed
SPR-02 | Employee Management | Implement employee master and lifecycle | US-EMP-001 | Completed | Nida Khan | Completed
SPR-02 | Employee Management | Implement employee master and lifecycle | US-EMP-002 | Completed | Nida Khan | Completed
SPR-02 | Employee Management | Implement employee master and lifecycle | US-EMP-003 | Completed | Nida Khan | Completed
SPR-02 | Employee Management | Implement employee master and lifecycle | US-EMP-004 | Completed | Nida Khan | Completed
SPR-02 | Employee Management | Implement employee master and lifecycle | US-EMP-005 | Completed | Nida Khan | Completed
SPR-03 | Organization & Workforce | Implement departments, roles and work statuses | US-DEPT-001 | Completed | Nida Khan | Completed
SPR-03 | Organization & Workforce | Implement departments, roles and work statuses | US-ROLE-001 | Completed | Nida Khan | Completed
SPR-03 | Organization & Workforce | Implement departments, roles and work statuses | US-WORK-001 | Completed | Nida Khan | Completed
SPR-04 | Attendance & Leave | Implement attendance and leave management | US-ATT-001 | Completed | Nida Khan | Completed
SPR-04 | Attendance & Leave | Implement attendance and leave management | US-ATT-002 | Completed | Nida Khan | Completed
SPR-04 | Attendance & Leave | Implement attendance and leave management | US-ATT-003 | Completed | Nida Khan | Completed
SPR-04 | Attendance & Leave | Implement attendance and leave management | US-LEAVE-001 | Completed | Nida Khan | Completed
SPR-04 | Attendance & Leave | Implement attendance and leave management | US-LEAVE-002 | Completed | Nida Khan | Completed
SPR-04 | Attendance & Leave | Implement attendance and leave management | US-LEAVE-003 | Completed | Nida Khan | Completed
SPR-05 | Performance & PIP | Implement performance and PIP management | US-PERF-001 | Completed | Nida Khan | Completed
SPR-05 | Performance & PIP | Implement performance and PIP management | US-PERF-002 | Completed | Nida Khan | Completed
SPR-05 | Performance & PIP | Implement performance and PIP management | US-PIP-001 | Completed | Nida Khan | Completed
SPR-05 | Performance & PIP | Implement performance and PIP management | US-PIP-002 | Completed | Nida Khan | Completed
SPR-06 | Learning & Development | Implement training management | US-TRAIN-001 | Completed | Nida Khan | Completed
SPR-06 | Learning & Development | Implement training management | US-TRAIN-002 | Completed | Nida Khan | Completed
SPR-06 | Learning & Development | Implement training management | US-TRAIN-003 | Completed | Nida Khan | Completed
SPR-06 | Learning & Development | Implement training management | US-TRAIN-004 | Completed | Nida Khan | Completed
SPR-07 | Recruitment | Implement recruitment lifecycle APIs | US-REC-001 | Completed | Nida Khan | Completed
SPR-07 | Recruitment | Implement recruitment lifecycle APIs | US-REC-002 | Completed | Nida Khan | Completed
SPR-07 | Recruitment | Implement recruitment lifecycle APIs | US-REC-003 | Completed | Nida Khan | Completed
SPR-07 | Recruitment | Implement recruitment lifecycle APIs | US-REC-004 | Completed | Nida Khan | Completed
SPR-07 | Recruitment | Implement recruitment lifecycle APIs | US-REC-005 | Completed | Nida Khan | Completed
SPR-07 | Recruitment | Implement recruitment lifecycle APIs | US-REC-006 | Completed | Nida Khan | Completed
SPR-07 | Recruitment | Implement recruitment lifecycle APIs | US-REC-007 | Completed | Nida Khan | Completed
SPR-07 | Recruitment | Implement recruitment lifecycle APIs | US-REC-008 | Completed | Nida Khan | Completed
SPR-08 | Analytics | Implement HR analytics APIs | US-AN-001 | Completed | Nida Khan | Completed
SPR-08 | Analytics | Implement HR analytics APIs | US-AN-002 | Completed | Nida Khan | Completed
SPR-08 | Analytics | Implement HR analytics APIs | US-AN-003 | Completed | Nida Khan | Completed
SPR-08 | Analytics | Implement HR analytics APIs | US-AN-004 | Completed | Nida Khan | Completed
SPR-08 | Analytics | Implement HR analytics APIs | US-AN-005 | Completed | Nida Khan | Completed
SPR-08 | Analytics | Implement HR analytics APIs | US-AN-006 | Completed | Nida Khan | Completed
SPR-08 | Analytics | Implement HR analytics APIs | US-AN-007 | Completed | Nida Khan | Completed
SPR-09 | Frontend & BI | Build React frontend and integrate dashboards | US-AN-001 | Planned | Nida Khan | Planned
SPR-10 | Recruitment Integration | Implement recruitment-to-employee transition | US-REC-009 | Planned | Nida Khan | Planned

## Traceability
Trace ID | BRD Requirement | FRD Requirement | Process ID | User Story | Acceptance Criteria | API / System | Status
TR-001 | BR-001 | FR-EMP-001 | P-01 | US-EMP-001 | AC-EMP-001 | /api/employees | Implemented
TR-002 | BR-001 | FR-EMP-002 | P-01 | US-EMP-002 | AC-EMP-003 | /api/employees | Implemented
TR-003 | BR-001 | FR-EMP-003 | P-01 | US-EMP-003 | AC-EMP-004 | /api/employees | Implemented
TR-004 | BR-003 | FR-EMP-004 | P-01 | US-EMP-004 | AC-EMP-005 | /api/employees/:id/status | Implemented
TR-005 | BR-004 | FR-EMP-005 | P-03 | US-EMP-005 | AC-EMP-006; AC-EMP-007; AC-EMP-008; AC-EMP-009 | /api/employees | Implemented
TR-006 | BR-002 | FR-DEPT-001 | P-02 | US-DEPT-001 | AC-DEPT-001 | /api/departments | Implemented
TR-007 | BR-002 | FR-ROLE-001 | P-02 | US-ROLE-001 | AC-ROLE-001 | /api/job-roles | Implemented
TR-008 | BR-005 | FR-WORK-001 | P-03 | US-WORK-001 | AC-WORK-001 | /api/work-statuses | Implemented
TR-009 | BR-006 | FR-ATT-001 | P-04 | US-ATT-001 | AC-ATT-001; AC-ATT-002 | /api/attendance | Implemented
TR-010 | BR-006 | FR-ATT-002 | P-04 | US-ATT-002 | AC-ATT-003 | /api/attendance | Implemented
TR-011 | BR-007 | FR-LEAVE-001 | P-05 | US-LEAVE-003 | AC-LEAVE-003 | /api/leave-types | Implemented
TR-012 | BR-007 | FR-LEAVE-002 | P-05 | US-LEAVE-001 | AC-LEAVE-001 | /api/leave-requests | Implemented
TR-013 | BR-007 | FR-LEAVE-003 | P-05 | US-LEAVE-002 | AC-LEAVE-002 | /api/leave-requests | Implemented
TR-014 | BR-008 | FR-PERF-001 | P-06 | US-PERF-001 | AC-PERF-001 | /api/performance-reviews | Implemented
TR-015 | BR-008 | FR-PERF-002 | P-06 | US-PERF-002 | AC-PERF-002 | /api/performance-reviews | Implemented
TR-016 | BR-009 | FR-PIP-001 | P-07 | US-PIP-001 | AC-PIP-001 | /api/pips | Implemented
TR-017 | BR-009 | FR-PIP-002 | P-07 | US-PIP-002 | AC-PIP-002 | /api/pips | Implemented
TR-018 | BR-010 | FR-TRAIN-001 | P-08 | US-TRAIN-001 | AC-TRAIN-001 | /api/training-programs | Implemented
TR-019 | BR-010 | FR-TRAIN-002 | P-08 | US-TRAIN-002 | AC-TRAIN-002 | /api/employee-training | Implemented
TR-020 | BR-010 | FR-TRAIN-003 | P-08 | US-TRAIN-003 | AC-TRAIN-003 | /api/employee-training | Implemented
TR-021 | BR-010 | FR-TRAIN-004 | P-08 | US-TRAIN-004 | AC-TRAIN-004 | /api/analytics/training | Implemented
TR-022 | BR-011 | FR-REC-001 | P-09 | US-REC-001 | AC-REC-001 | /api/candidates | Implemented
TR-023 | BR-011 | FR-REC-002 | P-09 | US-REC-002 | AC-REC-002 | /api/candidates | Implemented
TR-024 | BR-012 | FR-REC-003 | P-10 | US-REC-003 | AC-REC-003; AC-REC-004 | /api/job-applications | Implemented
TR-025 | BR-012 | FR-REC-004 | P-10 | US-REC-004 | AC-REC-005 | /api/job-applications | Implemented
TR-026 | BR-013 | FR-REC-005 | P-11 | US-REC-005 | AC-REC-006 | /api/interviews | Implemented
TR-027 | BR-013 | FR-REC-006 | P-11 | US-REC-006 | AC-REC-007 | /api/interviews | Implemented
TR-028 | BR-014 | FR-REC-007 | P-12 | US-REC-007 | AC-REC-008; AC-REC-010 | /api/job-offers | Implemented
TR-029 | BR-014 | FR-REC-008 | P-12 | US-REC-008 | AC-REC-009 | /api/job-offers | Implemented
TR-030 | BR-015 | FR-REC-010 | P-13 | US-REC-009 | AC-REC-011 | Recruitment + Employees | Planned
TR-031 | BR-016 | FR-AN-001 | P-14 | US-AN-001 | AC-AN-001 | /api/analytics/overview | Implemented
TR-032 | BR-017 | FR-AN-002 | P-14 | US-AN-002 | AC-AN-002 | /api/analytics/departments | Implemented
TR-033 | BR-018 | FR-AN-003 | P-14 | US-AN-003 | AC-AN-003 | /api/analytics/attendance | Implemented
TR-034 | BR-018 | FR-AN-004 | P-14 | US-AN-004 | AC-AN-004 | /api/analytics/leave | Implemented
TR-035 | BR-018 | FR-AN-005 | P-14 | US-AN-005 | AC-AN-005 | /api/analytics/performance | Implemented
TR-036 | BR-018 | FR-AN-006 | P-14 | US-AN-006 | AC-AN-006 | /api/analytics/training | Implemented
TR-037 | BR-018 | FR-AN-007 | P-14 | US-AN-007 | AC-AN-007 | /api/analytics/recruitment | Implemented
TR-038 | BR-019 | FR-API-001 | P-15 | US-API-001 | AC-API-001 | REST APIs | Implemented
TR-039 | BR-020 | FR-API-002 | P-15 | US-API-002 | AC-API-002 | REST APIs | Implemented
TR-040 | BR-019 | FR-DB-001; FR-DB-002 | P-15 | US-API-003 | AC-API-003 | PostgreSQL | Implemented
TR-041 | BR-020 | FR-SEC-001; FR-SEC-002 | P-15 | US-API-004 | AC-API-004 | Backend / .env | Implemented

## Jira Import
Issue Type | Summary | Description | Epic Name | Priority | Story Points | Status | Labels | Component | Business Owner
Epic | Workforce & Employee Management | Employee, department, role and workforce-status management | EPIC-01 | High |  | Implemented | hr360;workforce | Employee Management | HR
Epic | Attendance & Leave | Attendance recording and leave management | EPIC-02 | High |  | Implemented | hr360;attendance;leave | Workforce Operations | HR
Epic | Performance & PIP | Performance review and improvement management | EPIC-03 | High |  | Implemented | hr360;performance | Performance | HR
Epic | Learning & Development | Training program and employee learning management | EPIC-04 | Medium |  | Implemented | hr360;training | Learning | HR
Epic | Recruitment | Candidate, application, interview and offer management | EPIC-05 | High |  | Implemented | hr360;recruitment | Recruitment | HR / Operations / Finance
Epic | Analytics & BI | HR analytics and management reporting | EPIC-06 | Critical |  | Implemented | hr360;analytics;bi | Analytics | HR
Epic | Platform API & Data | API, database integrity and security requirements | EPIC-07 | High |  | Implemented | hr360;api;database | Platform | HR
Story | US-EMP-001 — Create employee record | As an HR user, I want to create an employee record so that employee information is centrally maintained. | EPIC-01 | High | 5 | Implemented | hr360;employee | Employee Management | HR
Story | US-EMP-002 — Retrieve employee information | As an HR user, I want to retrieve employee information so that I can view current workforce details. | EPIC-01 | High | 3 | Implemented | hr360;employee | Employee Management | Operations
Story | US-EMP-003 — Update employee information | As an HR user, I want to update employee information so that employee records remain current. | EPIC-01 | High | 3 | Implemented | hr360;employee | Employee Management | Operations
Story | US-EMP-004 — Employee lifecycle status | As an HR user, I want to update employee lifecycle status so that employment changes are recorded accurately. | EPIC-01 | High | 3 | Implemented | hr360;employee;lifecycle | Employee Management | Operations
Story | US-EMP-005 — Department-specific active status | As an HR or business manager, I want department-specific active status calculated so that workforce activity is represented according to business rules. | EPIC-01 | Critical | 5 | Implemented | hr360;business-rule;active-status | Employee Management | HR
Story | US-DEPT-001 — Department management | As an HR user, I want to maintain departments so that employees and organizational reporting use valid department information. | EPIC-01 | High | 3 | Implemented | hr360;department | Organization | HR / Managers
Story | US-ROLE-001 — Job role management | As an HR user, I want to maintain job roles so that employees and recruitment activities use valid roles. | EPIC-01 | High | 3 | Implemented | hr360;job-role | Organization | HR
Story | US-WORK-001 — Work status management | As an HR user, I want to maintain work statuses so that employee workforce states are consistently recorded. | EPIC-01 | High | 3 | Implemented | hr360;work-status | Workforce | HR / Managers
Story | US-ATT-001 — Record attendance | As an HR or Operations user, I want to record employee attendance so that workforce attendance can be monitored. | EPIC-02 | High | 5 | Implemented | hr360;attendance | Attendance | HR / Managers
Story | US-LEAVE-001 — Submit leave request | As an employee or HR user, I want to submit a leave request so that leave can be formally recorded. | EPIC-02 | High | 5 | Implemented | hr360;leave | Leave | HR / Managers
Story | US-PERF-001 — Record performance review | As an HR or manager, I want to record performance reviews so that employee performance can be evaluated and tracked. | EPIC-03 | High | 5 | Implemented | hr360;performance | Performance | HR / Managers
Story | US-PIP-001 — Create PIP | As an HR or manager, I want to create a Performance Improvement Plan so that performance improvement activities are formally tracked. | EPIC-03 | High | 5 | Implemented | hr360;pip | Performance | HR / Training
Story | US-TRAIN-001 — Training program management | As an HR or training user, I want to maintain training programs so that available learning programs are centrally managed. | EPIC-04 | High | 3 | Implemented | hr360;training | Learning | HR / Training
Story | US-TRAIN-002 — Employee training enrollment | As an HR or training user, I want to enroll employees into training so that employee participation can be tracked. | EPIC-04 | High | 5 | Implemented | hr360;training | Learning | HR / Training
Story | US-REC-001 — Candidate management | As a recruiter, I want to create candidate records so that prospective employees can be managed through a centralized pipeline. | EPIC-05 | High | 5 | Implemented | hr360;candidate | Recruitment | HR / Management
Story | US-REC-003 — Job application management | As a recruiter, I want to create job applications so that candidates can be associated with specific job roles. | EPIC-05 | High | 5 | Implemented | hr360;application | Recruitment | Recruitment
Story | US-REC-005 — Interview scheduling | As a recruiter, I want to schedule interviews so that candidate interviews are formally managed. | EPIC-05 | High | 5 | Implemented | hr360;interview | Recruitment | Recruitment
Story | US-REC-007 — Job offer management | As a recruiter, I want to create job offers so that selected candidates can receive formal offers. | EPIC-05 | High | 5 | Implemented | hr360;offer | Recruitment | Recruitment
Story | US-REC-009 — Recruitment-to-employee transition | As an HR or recruiter, I want accepted offers to be traceable to employee onboarding so that the recruitment-to-employee lifecycle is connected. | EPIC-05 | Medium | 5 | Planned | hr360;onboarding | Recruitment | Recruitment
Story | US-AN-001 — HR overview analytics | As an HR or management user, I want an HR overview dashboard so that key workforce indicators can be monitored. | EPIC-06 | Critical | 5 | Implemented | hr360;analytics;dashboard | Analytics | Recruitment
Story | US-AN-002 — Department analytics | As a management user, I want department analytics so that workforce information can be analyzed by department. | EPIC-06 | High | 5 | Implemented | hr360;analytics;department | Analytics | Recruitment / Interviewer
Story | US-AN-003 — Attendance analytics | As an HR or management user, I want attendance analytics so that workforce attendance trends can be monitored. | EPIC-06 | High | 3 | Implemented | hr360;analytics;attendance | Analytics | Recruitment
Story | US-AN-007 — Recruitment analytics | As a recruitment manager, I want recruitment analytics so that candidate and hiring pipeline activity can be monitored. | EPIC-06 | High | 3 | Implemented | hr360;analytics;recruitment | Analytics | Recruitment
Story | US-API-001 — REST API services | As an application user, I want validated REST APIs so that HR360 transactions are processed consistently. | EPIC-07 | High | 5 | Implemented | hr360;api | Platform | HR / Recruitment
Story | US-API-003 — Database integrity | As an application owner, I want HR data persisted with referential integrity so that related records remain consistent. | EPIC-07 | High | 5 | Implemented | hr360;database;postgresql | Platform | Management / HR
Story | US-API-004 — Configuration security | As an application owner, I want sensitive configuration protected so that database credentials and secrets are not exposed. | EPIC-07 | Critical | 3 | Implemented | hr360;security | Platform | Management / HR
US-AN-003 | EPIC-06 | Analytics & BI | As an HR or management user, I want attendance analytics so that workforce attendance trends can be monitored. | High | 3 | Implemented | FR-AN-003 | /api/analytics/attendance | Management / HR
US-AN-004 | EPIC-06 | Analytics & BI | As an HR or management user, I want leave analytics so that leave utilization can be monitored. | Medium | 3 | Implemented | FR-AN-004 | /api/analytics/leave | Management / HR
US-AN-005 | EPIC-06 | Analytics & BI | As an HR or management user, I want performance analytics so that employee performance information can be analyzed. | Medium | 3 | Implemented | FR-AN-005 | /api/analytics/performance | Management / HR
US-AN-006 | EPIC-06 | Analytics & BI | As an HR or management user, I want training analytics so that employee development activity can be analyzed. | Medium | 3 | Implemented | FR-AN-006 | /api/analytics/training | Management / HR
US-AN-007 | EPIC-06 | Analytics & BI | As a recruitment manager, I want recruitment analytics so that candidate and hiring pipeline activity can be monitored. | High | 3 | Implemented | FR-AN-007 | /api/analytics/recruitment | Recruitment / Management
US-API-001 | EPIC-07 | Platform API & Data | As an application user, I want validated REST APIs so that HR360 transactions are processed consistently. | High | 5 | Implemented | FR-API-001 | REST APIs | Application Owner
US-API-002 | EPIC-07 | Platform API & Data | As an application user, I want invalid requests to return controlled errors so that data quality and system reliability are maintained. | High | 3 | Implemented | FR-API-002 | REST APIs | Application Owner
US-API-003 | EPIC-07 | Platform API & Data | As an application owner, I want HR data persisted with referential integrity so that related records remain consistent. | High | 5 | Implemented | FR-DB-001 / FR-DB-002 | PostgreSQL | Application Owner
US-API-004 | EPIC-07 | Platform API & Data | As an application owner, I want sensitive configuration protected so that database credentials and secrets are not exposed. | Critical | 3 | Implemented | FR-SEC-001 / FR-SEC-002 | Backend / .env | Application Owner